## Site List with Labor Budget
Amazon Asset Tagging Project -Site List with Labor Budget | [6 empty] | 2022-06-19
Region | Location | Address | City | State | Zip | SF | Labor Budget | Labor Hours | Days for 2 person team @ 9 hours/day | Days for 3 person team @ 9 hours/day
NE | ACY5 | 2277 Center Square Road | Logan Township | NJ | 8085 | 203250 | 2456.4395 | 49.1288 | 2.7294 | 1.8196
NE | ACY8 | 8 Campus Drive | Logan Township | NJ | 8016 | 253500 | 3063.7512 | 61.275 | 3.4042 | 2.2694
SE | ATL6 | 4200 North Commerce | East Point | GA | 30344 | 301200 | 3640.244 | 72.8049 | 4.0447 | 2.6965
NE | BDL5 | 29 Research Parkway | Wallingford | CT | 6492 | 184875 | 2234.3629 | 44.6873 | 2.4826 | 1.6551
SE | BNA5 | 50 Airways Blvd | Nashville | TN | 37217 | 206474 | 2495.4042 | 49.9081 | 2.7727 | 1.8484
SE | BNA9 | 271 Mason Road | La Vergne | TN | 37086 | 850000 | 10272.9329 | 205.4587 | 11.4144 | 7.6096
NE | BOS4 | 1 National Street | Milford | MA | 1757 | 300000 | 3625.741 | 72.5148 | 4.0286 | 2.6857
NE | BOS5 | 1000 Technology Center Dr | Stoughton | MA | 2702 | 332676 | 4020.6567 | 80.4131 | 4.4674 | 2.9783
MW | BUF5 | 4201 Walden Avenue | Lancaster | NY | 14086 | 502792 | 6076.6453 | 121.5329 | 6.7518 | 4.5012
NE | BWI5 | 5501 Holabird Ave | Baltimore City | MD | 21224 ‎ | 346408 | 4186.619 | 83.7324 | 4.6518 | 3.1012
NE | CDW5 | 380 Middlesex Ave | Carteret | NJ | 7008 | 810343 | 9793.6462 | 195.8729 | 10.8818 | 7.2546
MW | CLE5 | 8686 Independence Parkway | Twinsburg | OH | 44087 | 248000 | 2997.2792 | 59.9456 | 3.3303 | 2.2202
SE | CLT5 | 7040 Northwinds Dr NW | Concord | NC | 28027 | 222577 | 2690.0219 | 53.8004 | 2.9889 | 1.9926
SE | CLT9 | 3620 Reeves Ridge Drive | Charlotte | NC | 28214 | 566800 | 6850.2334 | 137.0047 | 7.6114 | 5.0742
MW | CVG5 | 2285 Litton Lane | Hebron | KY | 41048 | 598000 | 7227.3104 | 144.5462 | 8.0303 | 5.3536
MW | CVG9 | 2305 Litton Lane | Hebron | KY | 41048 | 646468 | 7813.0851 | 156.2617 | 8.6812 | 5.7875
MW | DTW5 | 19991 Brownstown Center Drive Ste 900 | Brownstown | MI | 48192 | 366769 | 4432.698 | 88.654 | 4.9252 | 3.2835
NE | EWR5 | 301 Blair Road | Avenel | NJ | 7001 | 562230 | 6795.0012 | 135.9 | 7.55 | 5.0333
NE | EWR8 | 698 Route 46 | Teterboro | NJ | 7608 | 616992 | 7456.844 | 149.1369 | 8.2854 | 5.5236
NE | LDJ5 | 526 Gulf Ave | Staten Island | NY | 10314 | 975000 | 11783.6583 | 235.6732 | 13.093 | 8.7286
NE | LGA5 | 2205 State Route 27 | Edison | NJ | 8817 | 900022 | 10877.4889 | 217.5498 | 12.0861 | 8.0574
MW | MDW5 | 16825 Churnovic Lane | Crest Hill | IL | 60435 | 438150 | 5295.3948 | 105.9079 | 5.8838 | 3.9225
SE | MEM5 | 5155 Citation Drive | Memphis | TN | 38118 | 400000 | 4834.3214 | 96.6864 | 5.3715 | 3.581
SE | MGE5 | 235 Hog Mountain Road | Jefferson | GA | 30549 | 459134 | 5549.0033 | 110.9801 | 6.1656 | 4.1104
SE | MGE8 | 4905 Derrick Rd | Union City | GA | 30349 | 500000 | 6042.9017 | 120.858 | 6.7143 | 4.4762
MW | MKE5 | 11211 Burlington Road | Kenosha | WI | 53144 | 514011 | 6212.2359 | 124.2447 | 6.9025 | 4.6017
SE | MOB5 | 6735 Trippel Road | Theodore | AL | 36582 | 362942 | 4386.4457 | 87.7289 | 4.8738 | 3.2492
NE | MTN2 | 913 Old Philadelphia Road | Aberdeen | MD | 21001 | 634000 | 7662.3993 | 153.248 | 8.5138 | 5.6759
NE | MTN5 | 5300 Holabird AV | Baltimore | MD | 21224 | 247860 | 2995.5872 | 59.9117 | 3.3284 | 2.219
NE | MTN9 | 5300 Nottingham Drive | White Marsh | MD | 21236 | 585063 | 7070.9564 | 141.4191 | 7.8566 | 5.2377
MW | ORD9 | 23700 W. Bluff Road Bldg A | Channahon | IL | 60410 | 749554 | 9058.9623 | 181.1792 | 10.0655 | 6.7103
NE | OWD5 | 330 Bartlett Street | Northborough | MA | 1752 | 300000 | 3625.741 | 72.5148 | 4.0286 | 2.6857
NE | OWD9 | 350 Bartlett Street | Northborough | MA | 1752 | 300000 | 3625.741 | 72.5148 | 4.0286 | 2.6857
MW | PIT5 | 2250 Roswell Dr | Pittsburgh | PA | 15205 | 252540 | 3052.1488 | 61.043 | 3.3913 | 2.2609
NE | PNE5 | 18 Applegate Drive | Robbinsville | NJ | 8691 | 597594 | 7222.4036 | 144.4481 | 8.0249 | 5.3499
SE | RDU5 | 1805 TW Alexander Drive | Durham | NC | 27703 | 324838 | 3925.9282 | 78.5186 | 4.3621 | 2.9081
SE | RIC5 | 11600 N. Lakeridge Parkway | Ashland | VA | 23005 | 320853 | 3877.7663 | 77.5553 | 4.3086 | 2.8724
[6 empty] | 16980915 | 205228
SF